## Tabelle1
TravelMind Alpha Sprint Tasks |  |  |  |  | Overview
[8 empty] | Burn-down | 2
Day | Name | Category | Task | Completed on day | Day | # tasks | # completed on day | ideal | real
1 | Philipp | Project Setup | Create frontend project structure (React/Vite or chosen stack) | 1 | 0 | 0 | 0 | 165 | 165
1 | Philipp | Project Setup | Create backend Node.js + Express project | 1 | 1 | 33 | 28 | 132 | 137
1 | Philipp | Project Setup | Configure shared environment variables and .env.example | 1 | 2 | 33 | 38 | 99 | 99 | 99
1 | Philipp | Project Setup | Configure Git branches and folder conventions | 1 | 3 | 33 | 33 | 66
1 | Philipp | Project Setup | Install core dependencies (Leaflet, jsPDF, Axios/Fetch helpers, UUID) | 1 | 4 | 38 | 0 | 28
1 | Philipp | Project Setup | Configure linting and formatting (ESLint + Prettier) | 1 | 5 | 28 | 0 | 0
1 | Philipp | Project Setup | Define global CSS variables (colors, spacing, typography) | 1 | Summe | 165
1 | Philipp | Project Setup | Create responsive layout shell and navigation | 1
1 | Pascal | Backend Foundation | Create Express server bootstrap | 1
1 | Pascal | Backend Foundation | Configure CORS and JSON middleware | 1
1 | Pascal | Backend Foundation | Create /api/generate endpoint scaffold | 1
1 | Pascal | Backend Foundation | Create /api/regen endpoint scaffold | 1
1 | Pascal | Backend Foundation | Add DeepSeek API environment variable handling | 1
1 | Pascal | Backend Foundation | Implement backend timeout handling (15 s) | 1
1 | Pascal | Backend Foundation | Create shared API response format | 1
1 | Jacopo | Fast-Path Landing Screen | Create landing page layout | 1
1 | Jacopo | Fast-Path Landing Screen | Implement Mood selector button | 1
1 | Jacopo | Fast-Path Landing Screen | Create Mood bottom-sheet modal | 1
1 | Jacopo | Fast-Path Landing Screen | Add 6 mood tiles with icons and labels | 1
1 | Jacopo | Fast-Path Landing Screen | Add mood multi-select logic | 1
1 | Jacopo | Fast-Path Landing Screen | Implement selection confirmation animation | 1
1 | Jacopo | Fast-Path Landing Screen | Implement Duration selector button | 1
1 | Jacopo | Fast-Path Landing Screen | Create Duration bottom-sheet modal | 1
1 | Jacopo | Fast-Path Landing Screen | Add duration segmented options | 1
1 | Jacopo | Fast-Path Landing Screen | Implement Radius selector button | 1
1 | Jacopo | Fast-Path Landing Screen | Create Radius selector modal | 1
1 | Jacopo | Fast-Path Landing Screen | Add radius preset options | 1
1 | Jacopo | Fast-Path Landing Screen | Add “Anywhere” option behavior | 1
1 | Jacopo | UX + Accessibility | Add keyboard navigation support for selector buttons | 2
1 | Jacopo | UX + Accessibility | Add ARIA labels for mood/duration/radius options | 2
1 | Jacopo | UX + Accessibility | Ensure 72×72 dp button sizing | 2
1 | Jacopo | UX + Accessibility | Add focus states for all interactive elements | 2
1 | Jacopo | UX + Accessibility | Validate mobile responsiveness for landing page | 2
2 | Philipp | Selection Flow Logic | Implement sequential selector activation flow | 2
2 | Philipp | Selection Flow Logic | Persist selected values in component state | 2
2 | Philipp | Selection Flow Logic | Create trip brief chip row | 2
2 | Philipp | Selection Flow Logic | Add editable chips behavior | 2
2 | Philipp | Selection Flow Logic | Implement 300 ms delayed auto-trigger | 2
2 | Philipp | Selection Flow Logic | Implement long-press gesture detection | 2
2 | Philipp | Selection Flow Logic | Create extended options tab container | 2
2 | Philipp | Geolocation + Radius Logic | Integrate browser Geolocation API | 2
2 | Philipp | Geolocation + Radius Logic | Add geolocation loading state | 2
2 | Philipp | Geolocation + Radius Logic | Add geolocation fallback text input | 2
2 | Philipp | Geolocation + Radius Logic | Display detected city name in radius sheet | 2
2 | Philipp | Geolocation + Radius Logic | Handle denied location permission state | 2
2 | Philipp | Geolocation + Radius Logic | Handle geolocation timeout state | 2
2 | Pascal | Prompt Engineering Layer | Create promptBuilder.js | 2
2 | Pascal | Prompt Engineering Layer | Define prompt template structure | 2
2 | Pascal | Prompt Engineering Layer | Implement fast-path default injection | 2
2 | Pascal | Prompt Engineering Layer | Add parameter sanitization | 2
2 | Pascal | Prompt Engineering Layer | Append JSON schema instructions to prompt | 2
2 | Pascal | Prompt Engineering Layer | Create itinerary JSON schema definition | 2
2 | Pascal | DeepSeek Integration | Implement DeepSeek proxy service | 2
2 | Pascal | DeepSeek Integration | Connect /api/generate to DeepSeek | 2
2 | Pascal | DeepSeek Integration | Add API error handling | 2
2 | Pascal | DeepSeek Integration | Add one-retry logic for malformed responses | 2
2 | Pascal | DeepSeek Integration | Implement schema validation module | 2
2 | Pascal | DeepSeek Integration | Add structured backend error responses | 2
2 | Jacopo | Loading + Error States | Create loading screen UI | 2
2 | Jacopo | Loading + Error States | Add animated compass component | 2
2 | Jacopo | Loading + Error States | Add rotating status messages | 2
2 | Jacopo | Loading + Error States | Add indeterminate progress bar | 2
2 | Jacopo | Loading + Error States | Display Mood/Duration/Radius chips during loading | 2
2 | Jacopo | Loading + Error States | Create API failure screen | 2
2 | Jacopo | Loading + Error States | Add Retry button logic | 2
2 | Jacopo | Loading + Error States | Add Edit Parameters navigation logic | 2
3 | Philipp | Results Data Layer | Define frontend itinerary data model | 3
3 | Philipp | Results Data Layer | Create API response parser | 3
3 | Philipp | Results Data Layer | Add frontend schema safety checks | 3
3 | Philipp | Results Data Layer | Implement loading-to-results transition | 3
3 | Philipp | List View | Create Results screen layout | 3
3 | Philipp | List View | Create destination header section | 3
3 | Philipp | List View | Integrate Unsplash destination images | 3
3 | Philipp | List View | Add fallback placeholder image | 3
3 | Philipp | List View | Create day-card accordion component | 3
3 | Philipp | List View | Create itinerary stop card component | 3
3 | Philipp | List View | Add stop category chips | 3
3 | Philipp | List View | Add arrival time display | 3
3 | Philipp | List View | Add duration pill display | 3
3 | Philipp | List View | Add AI-generated description display | 3
3 | Philipp | List View | Add inter-stop travel note component | 3
3 | Jacopo | Map View | Install and configure Leaflet.js | 3
3 | Jacopo | Map View | Create map container component | 3
3 | Jacopo | Map View | Render stop markers from coordinates | 3
3 | Jacopo | Map View | Add numbered map pins | 3
3 | Jacopo | Map View | Draw route polyline | 3
3 | Jacopo | Map View | Add transport-adaptive line styles | 3
3 | Jacopo | Map View | Add map zoom controls | 3
3 | Jacopo | Map View | Add map recenter control | 3
3 | Jacopo | Map View | Implement List/Map tab switching | 3
3 | Jacopo | Map View | Preserve state between tab changes | 3
3 | Jacopo | Stop Detail Interactions | Create stop detail bottom sheet | 3
3 | Jacopo | Stop Detail Interactions | Open detail sheet on marker click | 3
3 | Jacopo | Stop Detail Interactions | Display stop metadata inside sheet | 3
3 | Jacopo | Stop Detail Interactions | Add swipe-down dismiss behavior | 3
3 | Jacopo | Stop Detail Interactions | Add tap-outside dismiss behavior | 3
3 | Jacopo | Responsiveness | Optimize Results page for mobile | 3
3 | Jacopo | Responsiveness | Validate 360 px viewport support | 3
3 | Jacopo | Responsiveness | Prevent horizontal scrolling | 3
4 |  | Single Stop Regeneration | Add refresh icon to stop cards
4 |  | Single Stop Regeneration | Connect /api/regen endpoint
4 |  | Single Stop Regeneration | Send contextual neighboring stops to AI
4 |  | Single Stop Regeneration | Replace only regenerated stop in state
4 |  | Single Stop Regeneration | Add inline loading spinner
4 |  | Single Stop Regeneration | Preserve rest of itinerary during regeneration
4 |  | Extended Wizard Flow | Create multi-step wizard container
4 |  | Extended Wizard Flow | Build Trip Type step
4 |  | Extended Wizard Flow | Build Location + Distance step
4 |  | Extended Wizard Flow | Build Duration step
4 |  | Extended Wizard Flow | Build Budget step
4 |  | Extended Wizard Flow | Build Traveller Group step
4 |  | Extended Wizard Flow | Build Transport Mode step
4 |  | Extended Wizard Flow | Build Review & Confirm screen
4 |  | Extended Wizard Flow | Add inline validation messages
4 |  | Extended Wizard Flow | Disable navigation on invalid inputs
4 |  | Extended Wizard Flow | Add inline edit navigation from review page
4 |  | Surprise Me Mode | Create Surprise Me CTA
4 |  | Surprise Me Mode | Generate random valid parameter combinations
4 |  | Surprise Me Mode | Trigger automatic itinerary generation
4 |  | Surprise Me Mode | Bypass wizard and selectors
4 |  | localStorage Persistence | Create localStorage manager utility
4 |  | localStorage Persistence | Implement itinerary auto-save
4 |  | localStorage Persistence | Generate UUID-v4 storage keys
4 |  | localStorage Persistence | Save metadata + itinerary payload
4 |  | localStorage Persistence | Add 24 h TTL handling for trip brief state
4 |  | localStorage Persistence | Prevent coordinate persistence
4 |  | localStorage Persistence | Handle quota exceeded errors
4 |  | My Trips Screen | Create My Trips page layout
4 |  | My Trips Screen | Load saved itineraries from storage
4 |  | My Trips Screen | Create trip history cards
4 |  | My Trips Screen | Display destination thumbnail and metadata
4 |  | My Trips Screen | Add search/filter input
4 |  | My Trips Screen | Implement real-time filtering
4 |  | My Trips Screen | Add empty state UI
4 |  | My Trips Screen | Add delete itinerary action
4 |  | My Trips Screen | Add delete confirmation modal
4 |  | My Trips Screen | Add swipe-to-delete behavior on mobile
5 |  | PDF Export | Integrate jsPDF
5 |  | PDF Export | Create PDF layout template
5 |  | PDF Export | Export destination header image
5 |  | PDF Export | Export trip metadata
5 |  | PDF Export | Export day-by-day itinerary content
5 |  | PDF Export | Add generation-date footer
5 |  | PDF Export | Trigger browser PDF download
5 |  | Shareable Links | Encode itinerary JSON as Base64
5 |  | Shareable Links | Generate shareable URL
5 |  | Shareable Links | Implement copy-to-clipboard functionality
5 |  | Shareable Links | Add success toast notification
5 |  | Shareable Links | Parse itinerary from shared URL
5 |  | Performance + Reliability | Optimize API loading performance
5 |  | Performance + Reliability | Optimize map rendering performance
5 |  | Performance + Reliability | Verify 15-second API timeout behavior
5 |  | Performance + Reliability | Verify stop regeneration under 10 seconds
5 |  | Performance + Reliability | Test fallback image rendering
5 |  | Performance + Reliability | Test graceful API failures
5 |  | Performance + Reliability | Test malformed JSON handling
5 |  | Performance + Reliability | Verify recoverable UI states
5 |  | Accessibility + UX Validation | Verify WCAG contrast compliance
5 |  | Accessibility + UX Validation | Verify keyboard-only navigation
5 |  | Accessibility + UX Validation | Verify touch target sizes
5 |  | Accessibility + UX Validation | Validate loading and error message clarity
5 |  | Accessibility + UX Validation | Run responsive testing across breakpoints
5 |  | Accessibility + UX Validation | Test Chrome compatibility
5 |  | Accessibility + UX Validation | Test Firefox compatibility
5 |  | Accessibility + UX Validation | Test Safari compatibility